## HOW TO USE THIS FILE
Template provided by:
FrontStream is a leader in digital fundraising & donor engagement. Our BiddingForGood community of over 1.7 MILLION philanthropic shoppers has raised $561 MILLION for thousands of nonprofits & schools. Learn more: frontstream.com
with |  |  | Status
Not Started
| How to use this file: Put in the date of your event, and then suggested tasks and actions for every step of planning the event automatically fill in! However, you can also arrange and edit dates and their corresponding tasks/actions to suite your unique needs as you go along by inserting or deleting cells. While we've pre-calculated dates for you based on the suggested timeframe, you can overwrite the dates simply by entering a new date in the date field. Find even more great tips for hosting a successful fundraising event at frontstream.com |  | Contracted
In Progress
Completed
Stuck
On Hold

## AUCTION PLANNER
Template provided by:
FrontStream is a leader in digital fundraising and donor engagement. Our BiddingForGood community of over 1.7 MILLION philanthropic shoppers has raised $561 MILLION (and counting) for thousands of nonprofits and schools. Learn more at frontstream.com
with
| EVENT NAME | [YOUR FABULOUS EVENT NAME TO RAISE MORE FOR YOUR CAUSE!]
| EVENT DATE: | 2024-06-01
| EVENT TIME: | 8am - 1pm
| DAYS UNTIL EVENT: | 261
| LOCATION: | Location info
| Budget & Revenue Snapshot |  |  | Budget / Goal | Actual | Progress to Goal
|  |  | Event Budget | 75000
|  |  | Fundraising | 90000 | 11250 | 13% to goal
|  |  | Sponsorships | 5000 | 1000 | 20% to goal
|  |  | Ticket Sales | 25000 | 10000 | 40% to goal
|  |  | Donations | 10000 | 250 | 3% to goal
|  |  | Auction proceeds | 50000 |  | 0% to goal
|  |  | Software: | Have you checked out Panorama from FrontStream?
| Auction Planning Committee Members | 1 | Event Lead | Contact #1
|  | 2 | Auction Coordinator | Contact #2
|  | 3 | Vonlutneer coordinator | Contact #3
|  | 4 | Sponsorship Manager | Contact #4
|  | 5 | Finance Manager | Contact #5
|  | 6 | Entertainment Coordinator | Contact #6
|  | 7 | Promotion Leader | Contact #7
| Recommended timefame | DUE DATE | TASK | ACTION | NOTES / STATUS UPDATES | Owner | STATUS
365 | 9 Months - 1 Year Before | 2023-06-02 | Review last year's fundraising results | Note satisfaction or room for improvement on important event aspects: Budget, reaching your goal, sponsors, programing, & special guests |  |  | Not started
Logistics review: What went well; opportunities & ideas for improvement (Venue, location, dates)
Experience review: Participant, donor, & volunteer
335 | 9 Months - 1 Year Before | 2023-07-02 | Develop your event goals | When setting financial goals, be specific; in addition to gross revenue, determine what each aspect of the fundraiser will contribute: include auction revenue, credit/debit card revenue, cash donations, ticket sales, revenue from add-ons like raffles, etc. | Check out these great ideas for auction items. Auctions are a great way to raise more at any event. frontstream.com/auction-item-ideas |  | Not started
335 | 9 Months - 1 Year Before | 2023-07-02 | Determine your event budget | Get details down: list every aspect of the event that has an expense attached to it & assign a “not to exceed” dollar amount |  |  | Not started
275 | 9 Months - 1 Year Before | 2023-08-31 | Build your core event committee | Identity the people who will make up your event-planning committee; they will help you finalize goals, develop promotional content, execute promotion, choose a location (+ get the permits), & determine an event theme |  |  | Not started
275 | 9 Months - 1 Year Before | 2023-08-31 | Select an event location (Live Event Only) | The earlier you do this, the more choice you will have of locations in your budget range available for your best dates |  |  | Not started
261 | 9 Months - 1 Year Before | 2023-09-14 | Select an event date | Avoid conflict with other large events, if possible—including religious holidays, sporting events, & other functions in your area |  |  | Not Started
Secure necessary permits (think: city, town, or campus) IF you're planning a live event
251 | 9 Months - 1 Year Before | 2023-09-24 | Determine if you'll need additional resources or liability insurance (Live Event Only) | Additional resources for a live event include: Accommodations for volunteers |  |  | Not Started
|  |  |  | Janitorial staff/volunteers |  |  | Not Started
Security personnel
|  |  |  | Rental equipment (tables, chairs, sound system, projector, etc.) |  |  | Not Started
245 | 9 Months - 1 Year Before | 2023-09-30 | Locate professional help, if needed | Interview & hire any professional help you need, like an auctioneer, guest speaker or announcer, musicians or MCs, decorators, or caterers |  |  | Not Started
240 | 5 Months - 8 Months Before | 2023-10-05 | Select your fundraising software | The right fundraising software tools can make or break your event | Conisder how your fundraising software provider can help you reach a wider audience to raise more funds. For example: BiddingForGood by FrontStream connects organizations to a community of over 1.7 MILLION philanthropic shoppers. See how Medfield Coalition for Public Education raised 30% more by using the right fundraising tools: frontstream.com/MCPE-gala-auction |  | Not Started
|  |  |  | Confirm payment processor with eye for donor experience (a bad payment experience can mean you lose that donor or participant forever) | If you’re using FrontStream’s fundraising software, then our payment processor is included, & no action is required. We are the leaders in secure payment technology and charitable donation processing & distribution services for organizations of all types. Learn more about FrontStream's fundraising platform & how it simplifies payment processing for nonprofits: frontstream.com/Fundraising-Solution |  | Not Started
240 | 5 Months - 8 Months Before | 2023-10-05 | Activate Auction “Coming Soon” / “Save the Date” homepage | Create an Auction “Coming Soon” homepage with your fundraising software tools; this gives you the flexibility to start sharing your event URL in promotion materials *You can create this homepage even if you don’t have a specific date for the event nailed down yet. But once you have your date in place, make sure to turn “Coming Soon” to “Save the Date” | Need help creating your event? BiddingForGood by FrontStream Experts are ready to help! Chat with them now: frontstream.com/auction-expert-chat |  | Not Started
230 | 5 Months - 8 Months Before | 2023-10-15 | Finalize event theme | Review all aspects of your event & make sure they align with your theme; begin designing a slogan, logo, & visual identity for the event |  |  | Not Started
185 | 4 Months - 7 Months Before | 2023-11-29 | Create a promotion schedule | Decide how many emails you want to send to supporters & at what intervals Suggestion: For the first four to six months, send one email every two to three weeks; once you’re a little less than two months away from your event, start sending emails once a week | Fill in your promotion schedule in the section below. |  | Not Started
185 | 4 Months - 7 Months Before | 2023-11-29 | Create promotional materials | Start creating your event promotion materials; if you don’t have a staff designer, find a volunteer designer or consider hiring a freelancer (college students looking to build their creative portfolios are a great option!) Mail or email a Save the Date with a link to the event page for your entire list of potential participants |  |  | Not Started
169 | 5 Months - 8 Months Before | 2023-12-15 | Segment donors & create target lists of supporters | Segment donors & participants, preferably by their past giving behavior/frequency; the more you personalize your communications, the more supporters will feel “seen” & likely act For example: Who participated in your last event but not the one before that? Who participated two events ago but not during your last event? | Take a look at how FrontStream's powerful & intuitive donor management software helps nonprofits thrive frontstream.com/CRM-Made-Easy |  | Not Started
|  |  |  | Segment Group #1: Last year's participants | These are just ideas to get you started. Make them your own!
Segment Group #2: New donors
Segment Group #3: New volunteers
169 | 5 Months - 8 Months Before | 2023-12-15 | Send initial mail/email registration page & donation requests | Share the event page with registration & donation links on your homepage, emails, & solicitation letters to make it easy for supporters to donate time (participation) &/or funds |  |  | Not Started
169 | 5 Months - 8 Months Before | 2023-12-15 | Solidify sponsorship levels | Decide on sponsorship levels & benefits of each level |  |  | Not Started
153 | 5 Months - 8 Months Before | 2023-12-31 | Assemble an auction item & sponsorship-procurement team or individual & start recruiting sponsors | Create collateral highlighting the benefits of providing in-kind donations &/or sponsoring the event + include talking points for outreach; the more time you allocate here, the more items & sponsorships you'll get | Allow a minimum of three months to get sponsors & continue seeking them throughout the entire planning process. |  | Not Started
122 | 2 Months - 4 Months Before | 2024-01-31 | Track auction items & sponsorships | Keep a running list of auction item & sponsorship responses that you received or denied; track everything you accept | Unlock more in-kind donations for your event with BiddingForGood by FrontStream’s unique & vast directory of charitably conscious businesses that support fundraising events: frontstream.com/BFG-by-FrontStream |  | Not Started
|  |  |  | Sponsorship level 1: | Track how many sponsors are committed in this space so you can see how many spots you have left.
Sponsorship level 2:
Sponsorship level 3:
108 | 2 Months - 4 Months Before | 2024-02-14 | Begin uploading items & displaying sponsorships on your auction site | Assess catalog value of donated items & sold sponsorships; designate items for the online, live, or silent auctions; showcase unique items & experiences; write descriptions of each item & determine prices; upload clear, well-lit pictures of auction items + ensure that sponors' brand logos are visible on your event page & that you develop a plan for making them visible at the live event (if you're having one) |  |  | Not Started
87 | 2 Months - 4 Months Before | 2024-03-06 | Prepare press realeases | Find deadlines for local media & prepare press releases or "blurbs" for local listings; share links on social media | It's a good time to check in on the promotion schedule you put together & make any tweaks. |  | Not Started
87 | 2 Months - 4 Months Before | 2024-03-06 | Review event giveaways | Design & order any event giveaways |  |  | Not Started
87 | 2 Months - 4 Months Before | 2024-03-06 | Order all event merchandise and custom goods | Find a reputable website or local printing business that creates custom merchandise for nonprofits & businesses; see if they offer any deals when you order in bulk; provide your logo & any other useful information; approve design mock-ups before greenlighting |  |  | Not Started
77 | 2 Months - 4 Months Before | 2024-03-16 | Recruit more volunteers if needed (Live Event Only) | Take a look at your current volunteer task allotment to figure out where you need more hands on deck; create volunteer job descriptions for specific volunteer tasks; begin recruiting volunteers for specific day-before & day-of tasks centered on set up, registration, parking lot oversight, refreshments, checkout, awards, merchandise, etc. |  |  | Not Started
62 | 2 Months - 4 Months Before | 2024-03-31 | View location (Live Event Only) | Review floor plan with the venue |  |  | Not Started
62 | 2 Months - 4 Months Before | 2024-03-31 | Assess Wi-Fi connectivity (Live Event Only) | Conduct a WiFi connectivity assessment for mobile bidding on smartphones |  |  | Not Started
61 | 2 Months - 4 Months Before | 2024-04-01 | Finalize refreshments & activities (Live Event Only) | Meet with the caterer or refreshment company & finalize menus and amounts, timing, flow of serving, etc.; meet with the decorators on final décor & event set up, as well as the MC & other side-event offerings, if applicable |  |  | Not Started
47 | 1 Month - 2 Months Before | 2024-04-15 | Start on event signage (Live Event Only) | Begin design for event signage, table tents, event instructions, displays, event program, award presentations, speeches, etc. |  |  | Not Started
30 | 1 Month Before | 2024-05-02 | Item fulfillment plan | Figure out an item fulfillment plan for after the event, including shipping &/or pickup location(s) & time(s) |  |  | Not Started
21 | 1 Month Before | 2024-05-11 | Create schedules & packing list (Live Event Only) | Create a day-before schedule, including timing for moving everything you can to the event location. Create an event packing list, including any equipment that you will need. Begin packing anything you can. Create a day-of schedule including the start & end times of every activity. |  |  | Not Started
16 | 1 Month Before | 2024-05-16 | Secure all necessary event-day materials (Live Event Only) | Make sure you have everything you might need, like headsets for volunteers, an onsite printer & laptop, etc. |  |  | Not Started
16 | 1 Month Before | 2024-05-16 | Publish & preview auction items | Start previewing auction items on your event homepage by publishing items & using the Featured Items section on your page to highlight most desirable items; proofread all auction item descriptions for spelling & grammar |  |  | Not Started
6 | 1 Week Before | 2024-05-26 | Prepare volunteers and staff (Live Event Only) | Print day-of schedules for all volunteers & staff; make sure your core staff/volunteers will be able to answer any questions that might arise from the music/entertainment workers, venue staff, decorators, participants, vendors, etc.; remember to delegate/don’t carry the whole event yourself |  |  | Not Started
6 | 1 Week Before | 2024-05-26 | Make attendee packets (Live Event Only) | Make attendee/bidder packets (catalog, table number, program, nametag); create extras for "walk-up" attendees |  |  | Not Started
6 | 1 Week Before | 2024-05-26 | Remind supporters to continue reaching out to friends, family, coworkers, neighbors, etc. | Send out “It’s not too late to join!” email & social media blast |  |  | Not Started
0 | 1 Week Before | 2024-06-01 | Close online auction (Live Event Only) | If you're not offering mobile bidding to attendees, close your online auction no later than a day before the event; print bid sheets & catalogs if you're having a silent auction with items in the room; the bid sheets will reflect the highest bid from online bidders | We recommend mobile bidding at live events, as it makes post-event closeout much easier for both your team & auction winners; learn more about mobile bidding: frontstream.com/yay-mobile-bidding |  | Not Started
0 | Day of | 2024-06-01 | Set up registration & check-in stations (Live Event Only) | Set up registration & checkout stations with attendee packages; distribute event schedule to all staff & volunteers |  |  | Not Started
0 |  |  | Perform final run-through before guests arrive (Live Event Only) | Decorate location/venue or approve final décor by decorator; soundcheck AV systems |  |  | Not Started
0 |  |  | Call a volunteer group-huddle (Live Event Only) | Run through event schedule with volunteers at least one hour before event start time – it’s great to do this once everything is set up, so the overview is as realistic as possible | Here are 75 inspirational quotes about volunteering to share with your team: frontstream.com/volunteering-quotes |  | Not Started
0 |  |  | Check in with local media & photographers (Live Event Only) | Meet up with any local media personnel who may be covering the event so they can get quotes from you; make sure the photographer/videographer is all set and has access to great shots that will help with your promotion for next year’s event |  |  | Not Started
-3 |  |  | Display items (Live Event Only) | Set up live or silent auction items with signage & QR codes that lead to their item webpage (or, if you're not using mobile bidding, make sure to include bid sheets) |  |  | Not Started
-7 |  |  | Process payments & distribute items (Live Event Only) | Process payments & verify payments process successfully before you give winning bidders their items |  |  | Not Started
-7 | Within 7 days after auction | 2024-06-08 | Add shipping fees & process payments | If you're mailing auction items to online bidders/winners or guests who had to leave a live event early, calculate shipping fees & finalize processing of payments |  |  | Not Started
-7 | 1 Week After | 2024-06-08 | Give thanks | Thank absolutely everyone: volunteers, sponsors, & of course, supporters! Include highlights from the event: how much you raised, edited pictures, & highest bids; there is no such thing as showing too much appreciation | Check out 20 great Thank You letter ideas to send to donors: frontstream.com/thank-you-donors |  | Not Started
-7 | 1 Week After | 2024-06-08 | Follow-up auction | Run a follow-up auction online to sell any remaining items |  |  | Not Started
-7 | 1 Week After | 2024-06-08 | Orchestrate a final team meeting | Meet with your team to discuss successful aspects of the event & the points where you can improve for next year’s auction |  |  | Not Started
-7 | 1 Week After | 2024-06-08 | Item distribution | Ship, deliver, or arrange for pickup of any items according to the plan you made about a month ago |  |  | Not Started
-14 | 1-3 Week After | 2024-06-15 | Create auction recap document | Create a recap document of the entire event (if you’re next year’s chair, you’ll thank yourself); If someone else is taking over, you’ll be their hero! Reconcile your budget, expenses, & revenue | It's always a good idea to do this immediately after the event when everything is fresh. This makes reviewing the takeaways & ideas much easier for next year's event. |  | Not Started
-20 | 1-3 Week After | 2024-06-21 | Finalize all financial information | Determine how much you raised gross & net; make final payments if you have any open invoices still |  |  | Not Started
PROMOTION CALENDAR
| RECOMMENDED TIMELINE | DUE DATE | PROMOTION ITEM | CHANNEL | CONTENT | OWNER | STATUS
| 5 Months - 8 Months Before | 2023-10-05 | Activate an Event “Coming Soon” / “Save the Date” homepage | Website |  |  | Not Started
|  |  | Share "Coming Soon" on Social Channels | Facebook | Look for a fundraising software solution that offers unique ways to reach a wider audience and raise more funds. With FrontStream, nonprofits can choose to have their auctions and auction items highlighted on the BiddingForGood homepage so that they're front and center for our community of over 1.7 MILLION philanthropic shoppers, for example. |  | Not Started
|  |  |  | Instagram |  |  | Not Started
|  |  |  | Twitter |  |  | Not Started
|  |  |  | TikTok |  |  | Not Started
| 5 Months - 8 Months Before | 2023-10-05 | Develop a promotion schedule |  |  |  | Not Started
| 4 Months - 7 Months Before | 2023-11-29 | Create promotional materials |  |  |  | Not Started
| 5 Months - 8 Months Before | 2023-12-15 | Segment donors & create target lists of supporters |  |  |  | Not Started
| 5 Months - 8 Months Before | 2023-12-03 | Update "Coming Soon" page to your auction event page |  |  |  | Not Started
|  |  |  | Twitter |  |  | Not Started
|  |  |  | TikTok |  |  | Not Started
| 5 Months - 8 Months Before | 2023-12-08 | Send initial mail/email about upcoming event & donation requests | Email |  |  | Not Started
|  |  |  | Direct mail |  |  | Not Started
| ONGOING UNTIL EVENT | 2023-12-15 | Send second email | Email |  |  | Not Started
|  | 2023-12-22 | Send third email | Email |  |  | Not Started
|  | 2023-12-29 | Send fourth email | Email |  |  | Not Started
|  | 2024-01-05 | Send fifth email | Email |  |  | Not Started
|  | 2024-01-12 | Send sixth email | Email |  |  | Not Started
|  | 2024-01-19 | Send seventh email | Email |  |  | Not Started
|  | 2024-01-26 | Send eighth email | Email |  |  | Not Started
|  | 2024-02-02 | Send ninth email | Email |  |  | Not Started
|  | 2024-02-09 | Send tenth email | Email |  |  | Not Started
|  | 2024-02-16 | Send eleventh email | Email |  |  | Not Started
|  | 2024-02-23 | Send twelfth email | Email |  |  | Not Started
60 | 2 Months - 4 Months Before | 2024-04-02 | Prepare & send out press release |  | Find the media deadlines & prepare press release or “blurbs” for local listings |  | Not Started
|  |  | Create media list |  | Identify your target journalist & media outlets; craft a targeted message about why your event is important & its impact to secure interest |  | Not Started
Formulas:
DUE DATE = [DUE DATE, row above]+7

## USEFUL LINKS
GREAT GUIDES, CHECKLISTS, & ARTICLES TO IMPROVE YOUR FUNDRAISING
10 Secrets for a Successful Auction | frontstream.com/10-auction-secrets
160+ Auction Item & Fundraising Ideas | frontstream.com/auction-item-ideas
How In-Kind Donations Boost Fundraising | frontstream.com/in-kind-donations-boost
75 Inspiring Quotes About Volunteering to Motivate Your Team | frontstream.com/Volunteering-Quotes
Ultimate Cause Calendar | frontstream.com/Ultimate-Cause-Calendar
4 Checklists Every Event Planner Needs | frontstream.com/4-event-planning-checklists
How to Create an Effective Fundraising Calendar | frontstream.com/effective-fundraising-calendar
20 Engaging Donation Thank You Letters Ideas to Try | frontstream.com/Thank-You-Donors
Nonprofit's Guide to Donor Personas | frontstream.com/donor-personas-guide
35 Dazzling Fundraiser Theme Ideas to Try This Season | https://frontstream.com/35-fundraising-themes
10 Smart Ways to Diversify Your Fundraising Efforts | frontstream.com/Diversify-Your-Fundraising
RESEARCHING SOFTWARE OPTIONS
Run Auctions. Sell Tickets. Find New Bidders. Raise More with BiddingForGood. | frontstream.com/BFG-by-FrontStream | Everything you Need to Host a Successful Online, In-Person or Mobile Auction
Advertise your auctions to raise more funds for your cause | frontstream.com/biddingforgood-auction-advertising | With FrontStream, nonprofits can choose to have their auctions and auction items highlighted on the BiddingForGood homepage so that they're front and center for our community of over 1.7 MILLION philanthropic shoppers, for example
Unlock the power of peer-to-peer events with Panorama by FrontStream | frontstream.com/Fundraising-Solution | Chat with an expert to learn more about Panorama by FrontStream's end-to-end peer-to-peer solution helps you manage your nonprofit’s in-person or virtual walk, run or ride campaign including other mission-funding donation pages to promote maximum engagement and charitable giving
Turbo-power donor engagement efforts & saves countless hours on administrative tasks | frontstream.com/CRM-Made-Easy | - Follow all supporter activity in one centralized record — no manual import-export rigamarole - Manage event registration, donations, giving day campaigns, & volunteer activities in one place - Streamline ticketing & payment processing - Run unlimited auctions, peer-to-peer events & DIY campaigns
ADD YOUR OWN LINKS HERE